Forensai

AI Psychological Evaluation Platform

Project Management Plan   |   March 2026   |   Confidential

________________________________________________________________________

PROJECT OVERVIEW

Forensai is organized into six parallel workstreams: Product Development, Grant and Funding, Business Development, Compliance and Legal, Clinical Advisory, and Marketing and Community. Each workstream has a lead, defined milestones, and a set of active tasks. All workstreams feed into the master Kanban board.

________________________________________________________________________

WORKSTREAM 1: PRODUCT DEVELOPMENT

Phase 0 (Now - Month 2): Foundation

Tasks: Monorepo setup (Turborepo), core architecture, local PII engine prototype, basic document import, React UI scaffold

Owner: CTO

Milestone: Working PII detection demo

Phase 1 (Month 2-4): MVP Core Agents

Tasks: Ingestor agent, Test Data Analyst agent, Writer agent (basic), DSM-5-TR local database, document viewer, export to DOCX

Owner: CTO + 1 Senior Engineer

Milestone: End-to-end evaluation draft from test data input

Phase 2 (Month 4-6): Full Agent System

Tasks: Diagnostician agent, Legal Reviewer agent, Editor agent, Fact Checker agent, Orchestrator, approval gates UI, voice notes (Whisper)

Owner: Engineering team

Milestone: Complete 8-agent pipeline, beta-ready

Phase 3 (Month 6-9): Beta and Hardening

Tasks: Beta deployment to Founding Forensic Cohort (10-15 psychologists), feedback integration, kanban case management, audit trail, DOCX/PDF export polish

Owner: Engineering + Customer Success

Milestone: 10 paying beta customers

Phase 4 (Month 9-12): Group Practice and Compliance

Tasks: Multi-user support, group practice tier, SOC 2 Type II audit prep, EHR integration research, RAG system for style matching

Owner: Engineering + Compliance

Milestone: SOC 2 audit initiated, first group practice customer

________________________________________________________________________

WORKSTREAM 2: GRANT AND FUNDING

Month 1: Register SAM.gov, obtain UEI, register SBIR.gov

Month 1-2: Hire SBIR grant writer, draft Specific Aims page

Month 2-3: Submit NIMH SBIR Phase I application

Month 3: Submit AHRQ SBIR application

Month 4-6: Apply to Arnold Ventures and APF non-federal grants

Month 6: Apply to NSF SBIR (Human-Centered Computing)

Month 9: NIMH review scores received, revise and resubmit if needed

Month 9-12: If funded, begin Phase I research activities

Month 18: Begin Phase II application development

Owner: CEO + Grant Writer

Milestone: Phase I application submitted, at least one non-federal grant secured

________________________________________________________________________

WORKSTREAM 3: BUSINESS DEVELOPMENT

Month 1: Build Founding Forensic Cohort list (target: 50 ABPP-certified forensic psychologists)

Month 1-2: Launch outreach via FORENSIC-PSYCH listserv and LinkedIn

Month 2-3: First 5 beta customers signed

Month 3-6: Grow to 15 beta customers, begin converting to paid

Month 6: First paid revenue milestone ($5K MRR)

Month 9: 20-30 paying customers, referral program launched

Month 12: $25K+ MRR, group practice outreach begins

Conference calendar: AP-LS Annual Conference (March), APA Annual (August), NAN Annual (October), AFCC Annual (May)

Owner: CEO + CRO

Milestone: 10 paying customers by Month 6, $15K MRR by Month 9

________________________________________________________________________

WORKSTREAM 4: COMPLIANCE AND LEGAL

Month 1: Entity formation (Delaware C-Corp recommended for VC path), EIN, bank account

Month 1: HIPAA risk assessment (45 CFR 164.308), privacy policy, BAA template

Month 2: Terms of service, data processing agreement

Month 3: First BAA executed with a customer

Month 6: SOC 2 Type II readiness assessment

Month 9: SOC 2 audit firm engaged

Month 15-18: SOC 2 Type II report issued

Month 18+: HITRUST CSF gap assessment

Owner: COO + Compliance Counsel

Milestone: HIPAA compliant at launch, SOC 2 Type II by Month 18

________________________________________________________________________

WORKSTREAM 5: CLINICAL ADVISORY

Month 1: Identify and recruit 3 ABPP-certified forensic psychologists as advisors

Month 2: First advisory board meeting, review product requirements

Month 3-4: Advisors participate in PII detection validation protocol design

Month 5-6: Advisors review DSM-5-TR mapping accuracy

Month 7-9: Advisors lead beta evaluation review

Month 12: First peer-reviewed manuscript submitted (target: Law and Human Behavior or Psychological Assessment)

Owner: Chief Clinical Officer / CEO

Milestone: Advisory board formed by Month 2, manuscript submitted by Month 12

________________________________________________________________________

WORKSTREAM 6: MARKETING AND COMMUNITY

Month 1: Website live (forensai.com), waitlist capture

Month 1-2: LinkedIn presence, FORENSIC-PSYCH listserv introduction post

Month 2-3: Time Audit Calculator tool launched (how many unbillable hours do you spend on reports?)

Month 3-6: Beta cohort case study content

Month 6: Conference presence strategy confirmed (AP-LS and NAN)

Month 9: First customer case study published

Month 12: Speaking submission for AP-LS Annual Conference 2027

Owner: CRO + Marketing

Milestone: 500 waitlist signups by Month 3, first case study published by Month 9

________________________________________________________________________

MASTER MILESTONE TABLE

Key milestones by period across all workstreams:

Quarter 1 (Months 1-3): Foundation complete, PII engine prototype live, SAM.gov registered, SBIR Phase I application submitted, 5 beta users signed

Quarter 2 (Months 4-6): MVP complete with full agent system, 15 beta users active, first paid revenue ($5K MRR), HIPAA compliant at customer launch

Quarter 3 (Months 7-9): Full 8-agent pipeline deployed, 25 paying customers, SOC 2 readiness initiated, first NIMH grant score received

Quarter 4 (Months 10-12): Group practice tier launched, SOC 2 audit firm engaged, 50 customers, $15K MRR, first peer-reviewed manuscript submitted

Year 2: SOC 2 Type II report issued, $1M ARR pipeline established, seed raise closed, state hospital pilot launched

Year 3: Series A or strategic raise completed, $3M+ ARR, HITRUST CSF gap assessment initiated

________________________________________________________________________

DECISION GATES

Four explicit go/no-go decisions the leadership team must make at defined checkpoints:

Gate 1 (Month 3): Is the PII detection engine accurate enough for clinical use? If not, extend Phase 0 before moving to MVP agent development.

Gate 2 (Month 6): Are beta customers using the product daily? If NPS falls below 40 or DAU drops below 60%, pause new customer acquisition and fix retention before scaling.

Gate 3 (Month 9): Did we receive a fundable SBIR score (below 30th percentile)? If yes, prioritize resubmission. If no, pivot to angel or strategic raise.

Gate 4 (Month 12): Is the business on track for $500K ARR in Year 2? If yes, begin Series A preparation. If no, extend runway and focus on unit economics.

________________________________________________________________________

AGENT-ASSISTED DEVELOPMENT MODEL

Forensai uses AI coding agents to accelerate product development while keeping human engineers in control of quality, security, and clinical accuracy.

Implementation: Claude Code and Codex handle feature implementation from detailed, human-written specifications

Human ownership: Engineers own architecture decisions, security-critical code, and clinical logic review

Automation: Agents run CI/CD checks, write tests, and generate documentation

Task queue: The development team maintains an agent task queue -- a prioritized backlog of well-specified tasks formatted for agent execution

Review gate: Every agent-generated code change requires human review before merge

Target: 60-70% of feature code generated by agents, 100% human-reviewed