FORENSAI

MVP Scope, Architecture & Specification

Production-Grade Foundation for Continuous Development

Foundry SMB  |  March 21, 2026

Truck Irwin, CEO

PART 1: MVP SCOPE

What Ships vs. What Waits

# 1. MVP Definition

The Forensai MVP is the smallest product that a solo forensic psychologist can use to take a real case from document upload through a finalized, signed evaluation report. It must be production-grade: encrypted, auditable, HIPAA-compliant, and built on architecture that continues directly into future phases without rewrite.

The MVP targets one user type (solo forensic psychologist), one evaluation type (forensic criminal competency evaluation), and one platform (macOS). Windows and Linux follow immediately after launch validation.

## 1.1 MVP Success Criteria

- Solo clinician completes a full forensic evaluation report in under 2 hours (vs. 6–12 hours baseline)

- All PHI encrypted at rest and de-identified before any LLM API transmission

- Full audit trail from document upload through signed report

- Report output matches clinician’s writing voice (validated by beta cohort)

- Zero AI-initiated diagnoses — every diagnostic conclusion is clinician-selected

## 1.2 What Ships in MVP

### Core Workflow (End to End)

- Case creation from referral document upload

- Document upload: PDF, DOCX (up to 10 files, 200MB per case)

- Ingestor Agent: extract demographics, referral questions, test scores, behavioral observations, timeline

- Gate 1: data confirmation in split view (original doc left, structured data right)

- Diagnostician Agent: validity assessment, evidence mapping to DSM-5-TR criteria, differential diagnosis

- Gate 2: individual diagnostic decisions (Render / Rule Out / Defer) with clinical notes

- Writer Agent: full report generation with clinician voice matching

- Gate 3: review editor flags, attestation, finalize and export

- Report export: .docx and sealed PDF with SHA-256 hash

### Agents (All 4)

- Ingestor Agent — document parsing and structuring

- Diagnostician Agent — evidence mapping and validity assessment

- Writer Agent — voice-matched report generation

- Editor/Legal Reviewer Agent — vulnerability and consistency flags

### Infrastructure

- Electron desktop application (macOS first)

- SQLCipher encrypted local database

- Python sidecar for PII detection (Presidio + spaCy)

- Claude API integration with TLS pinning

- Auth0 authentication and license verification

- Stripe billing (single Professional tier: $149/mo or $1,249/yr)

- Auto-update with Ed25519 signature verification

- Sentry crash reporting (de-identified)

- Apple code signing and notarization

### Document Editor

- OnlyOffice Document Server (Community Edition, AGPL) embedded as local service for native OOXML editing

- AI-generated content marked with orange dashed callouts (Word comments + styled content blocks)

- Editor/Legal flags rendered as native Word track-changes comments

- Native .docx save (document is already OOXML) and sealed PDF export

### Security & Compliance

- HIPAA Safe Harbor de-identification (18 identifiers) via Python sidecar

- PII detection before every LLM API call

- SQLCipher AES-256 encryption at rest

- Attestation with clinician e-signature and timestamp

- Audit trail with configurable granularity

- CSP hardening, sandboxed renderer, no nodeIntegration

### Settings & Configuration

- Practice profile selection (Forensic Criminal for MVP)

- Diagnosis catalog configuration (enable/disable DSM-5-TR diagnoses)

- Instrument library configuration

- Writing style extraction from 3–5 uploaded sample reports

- Report template selection (single default forensic criminal template)

## 1.3 What Does NOT Ship in MVP

| Feature | Reason Deferred | Phase | Risk if Deferred |
| --- | --- | --- | --- |
| OnlyOffice Developer Edition | Community Edition (AGPL, free) ships in MVP; Developer Edition upgrade if commercial license needed | v1.1+ | Low — AGPL is fine for desktop app |
| Audio transcription (Whisper) | Adds Python binary size, most clinicians already have transcripts | v1.1 | Low — users paste transcripts |
| Psychometrist role | Single user MVP; RBAC architecture ships but role is disabled | v1.1 | None |
| Shared storage (network/cloud) | Solo practitioner focus; architecture prepared per ADR-001 | v1.1/v2.0 | None |
| Psycho-legal analysis (Dusky, M’Naghten) | Diagnostician focuses on DSM-5-TR mapping first; legal analysis adds complexity | v1.1 | Medium — forensic users want this |
| Testimony preparation export | Requires audit trail maturation | v1.2 | Low |
| Windows/Linux builds | macOS first for code signing pipeline; Electron is cross-platform | v1.0.1 | Medium — limits market |
| Offline mode | Requires sync architecture; MVP requires internet for LLM calls anyway | v2.0 | Low |
| Case search/filter | Simple case list sufficient for solo with <50 cases | v1.1 | Low |
| Custom instruments | Built-in instrument library covers 95% of forensic use cases | v1.2 | Low |
| Multi-case dashboard / Kanban | Overkill for solo practitioner with 3–5 active cases | v1.1 | Low |
| PHI Review Queue | PII detection is automated; manual review is friction that can be added if users request it | v1.1 | Low — automated PII is sufficient |

## 1.4 Document Editor: OnlyOffice Community Edition

The MVP ships with OnlyOffice Document Server (Community Edition) embedded as a local service inside the Electron application. This provides native OOXML document editing — the same format clinicians already know from Microsoft Word.

Rationale:

- The deliverable IS the document — court-filed evaluation reports must be flawless .docx with track changes, comments, headers, footers, section breaks, and page numbering

- OnlyOffice Community Edition is AGPL-licensed and free for self-hosted use; a desktop app running a local server qualifies

- Native OOXML editing means the document is never “exported” to .docx — it IS .docx from first keystroke

- Track changes natively distinguish AI-generated vs. clinician edits

- Editor/Legal Reviewer flags render as native Word comments — clinicians already know this workflow

- OnlyOffice Document Server runs as a local process (similar to the Python sidecar) on localhost, no Docker required for development

- If AGPL becomes a licensing concern at scale, Developer Edition ($1,500–$2,400/yr) is a clean upgrade path after revenue

PART 2: MVP ARCHITECTURE

Production-Grade from Day One

# 2. System Architecture

## 2.1 High-Level Architecture

Electron Main Process (Node.js)

├─ SQLCipher Database (encrypted local storage)

├─ Auth0 SDK (authentication + license check)

├─ Stripe SDK (subscription verification)

├─ LLM Gateway (Claude API, TLS-pinned)

├─ Auto-Updater (electron-updater + Ed25519)

└─ Python Sidecar (Unix socket JSON-RPC)

├─ PII Detection (Presidio + spaCy)

└─ Style Extraction (heuristic + Claude)

Electron Renderer (React, sandboxed)

├─ Case Explorer (tree component)

├─ OnlyOffice Editor (embedded, native OOXML)

├─ Gate 1/2/3 Workflows

├─ Writing Assistant (AI chat panel)

└─ Settings / Onboarding

## 2.2 Technology Stack

| Layer | Technology |
| --- | --- |
| Desktop Shell | Electron 30+ (Chromium + Node.js) |
| Frontend Framework | React 18 + TypeScript |
| State Management | Zustand (lightweight, no boilerplate) |
| Document Editor | OnlyOffice Document Server (Community Edition, embedded local service) |
| Database | better-sqlite3 + SQLCipher (AES-256) |
| ORM / Query | Drizzle ORM (TypeScript-native, zero overhead) |
| IPC Security | contextBridge + preload scripts (no nodeIntegration) |
| Python Sidecar | Python 3.11 + Presidio + spaCy (en_core_web_lg) |
| Sidecar Protocol | JSON-RPC 2.0 over Unix socket |
| LLM Provider | Anthropic Claude API (claude-sonnet-4-20250514) |
| Authentication | Auth0 (OAuth 2.0 PKCE, machine-to-machine) |
| Billing | Stripe (embedded checkout, webhook verification) |
| Build System | Vite (renderer) + electron-builder (packaging) |
| Testing | Vitest (unit) + Playwright (E2E) + pytest (sidecar) |
| CI/CD | GitHub Actions |
| Crash Reporting | Sentry (de-identified, no PHI) |
| Auto-Update | electron-updater (Ed25519 signed) |
| Code Signing | Apple Developer ID + Notarization |

## 2.3 Process Architecture

The application runs as four OS processes:

Process 1: Electron Main (Node.js)

- Manages application lifecycle, window management, IPC routing

- Owns the SQLCipher database connection (single writer)

- Spawns and monitors Python sidecar

- Makes all external API calls (Claude, Auth0, Stripe, Sentry)

- No direct access from renderer — everything goes through contextBridge

Process 2: Electron Renderer (Chromium, sandboxed)

- React application with OnlyOffice editor iframe

- Sandboxed: no Node.js access, no file system access

- Communicates exclusively via IPC to main process

- CSP: no inline scripts, no eval, whitelisted CDN origins only

Process 3: OnlyOffice Document Server (Local)

- Spawned by main process at startup as a local HTTP service on localhost

- Serves the OnlyOffice editor UI, loaded in an iframe in the renderer

- Handles document open/save events via OnlyOffice Document API callbacks

- Macros and external plugins disabled for security

- Auto-save every 30 seconds to SQLCipher-managed document store

- Health-checked; auto-restarted on failure

Process 4: Python Sidecar

- Spawned by main process at startup

- Listens on random Unix socket (path known only to main process)

- Handles PII detection and style extraction

- Health-checked every 30 seconds; auto-restarted on failure

- Bundled as PyInstaller frozen executable (no Python runtime dependency for end user)

## 2.4 Data Flow: Document to Report

Step 1: Upload

- Clinician uploads PDF/DOCX files via renderer

- Renderer sends file bytes to main process via IPC

- Main process stores raw file in SQLCipher blob storage

Step 2: PII Detection

- Main process extracts text from documents (pdf-parse for PDF, mammoth for DOCX)

- Text sent to Python sidecar for PII detection

- Sidecar returns de-identified text + entity map

- Both original and de-identified versions stored in database

Step 3: Ingestor Agent

- De-identified text sent to Claude API with Ingestor system prompt

- Claude returns structured JSON case record

- Main process re-identifies output using entity map (replacing placeholders with originals)

- Structured case record stored in database

Step 4: Gate 1 — Data Confirmation

- Renderer displays split view: original documents (left) + extracted data (right)

- Clinician confirms, corrects, or flags each data category

- Confirmed data saved to database; audit trail logged

Step 5: Diagnostician Agent

- Confirmed case data de-identified and sent to Claude API

- Claude returns evidence maps, validity assessment, differential diagnosis

- Results re-identified and stored

Step 6: Gate 2 — Diagnostic Decision

- Renderer displays diagnosis cards with evidence maps

- Clinician selects Render / Rule Out / Defer for each diagnosis (no “Accept All”)

- Clinical notes recorded per decision

Step 7: Writer Agent

- Gate 1 data + Gate 2 decisions + style rules sent to Claude API (de-identified)

- Claude streams report sections

- Report re-identified, saved as .docx, and opened in OnlyOffice editor

Step 8: Editor/Legal Reviewer Agent

- Generated report sent to Claude API for vulnerability review

- Flags returned and rendered as native Word comments in OnlyOffice

Step 9: Gate 3 — Attestation

- Clinician reviews each flag (accept/dismiss/edit)

- Signs attestation (e-signature + timestamp)

- Report finalized: locked, hashed (SHA-256), exported as .docx and sealed PDF

## 2.5 Database Schema (MVP Subset)

The full 14-table schema from the engineering spec ships in MVP, but only the following tables are actively used:

| Table | MVP Usage |
| --- | --- |
| users | Single clinician record; role, license, preferences |
| cases | Case header: evaluee name, DOB, type, status, current gate |
| case_documents | Uploaded files: binary blob, extracted text, de-identified text |
| ingestor_results | Structured JSON from Ingestor Agent |
| diagnostic_decisions | Gate 2 clinician decisions per diagnosis |
| generated_reports | Report text, version history, editor flags |
| audit_trail | All case events with timestamps and user |
| style_rules | Pre-computed writing guidance from sample analysis |
| diagnosis_catalog | DSM-5-TR diagnoses (seeded) |
| instrument_library | Test instruments and scoring info (seeded) |
| report_templates | Report section ordering and template content |
| practice_profiles | Practice type configurations |

Tables for sessions, diagnosis_instrument_mappings, and shared storage metadata exist in schema but are unused in MVP. This avoids migration pain when Phase 2 activates them.

## 2.6 IPC Contract Summary

All communication boundaries use typed contracts. The full IPC spec (02_ipc_api_contracts.md) defines 47 endpoints across 4 boundaries. For MVP, the active endpoints are:

Boundary 1: Main ↔ Renderer (Electron IPC via contextBridge)

- case:create, case:list, case:get, case:updateStatus

- document:upload, document:getText, document:list

- agent:runIngestor, agent:runDiagnostician, agent:runWriter, agent:runEditor

- gate1:getData, gate1:confirm, gate1:save

- gate2:getDiagnoses, gate2:saveDecision

- gate3:getFlags, gate3:resolveFlag, gate3:signAttestation, gate3:finalize

- report:exportDocx, report:exportPdf

- settings:get, settings:update

- auth:login, auth:logout, auth:getProfile

Boundary 2: Main ↔ Python Sidecar (JSON-RPC over Unix socket)

- pii/detect — de-identify text (single document)

- pii/detect-batch — de-identify multiple documents

- style/extract — analyze writing samples

- health — sidecar health check

Boundary 3: Main ↔ Claude API (HTTPS)

- 4 agent calls: ingestor, diagnostician, writer, editor

- All calls use de-identified text only

- Response streaming for writer agent

Boundary 4: Main ↔ External Services

- Auth0: login flow, token refresh, license check

- Stripe: subscription status verification

- Sentry: crash reports (no PHI)

- electron-updater: update check + download

## 2.7 Security Architecture

| Layer | Implementation |
| --- | --- |
| Encryption at Rest | SQLCipher AES-256-CBC; key from passphrase + Argon2id KDF |
| PII Detection | Microsoft Presidio + spaCy (18 HIPAA identifiers); runs locally in sidecar |
| IPC Security | contextBridge whitelist; no nodeIntegration; sandbox: true |
| CSP | default-src ‘self’; no inline scripts; no eval; CDN whitelist for fonts |
| API Security | TLS 1.3 with certificate pinning for api.anthropic.com |
| API Key Storage | macOS Keychain via electron safeStorage API |
| Code Signing | Apple Developer ID + notarization; auto-update Ed25519 verification |
| Audit Trail | Immutable append-only log; clinician cannot delete entries |
| Auto-Lock | Configurable inactivity timeout (default 15 minutes) |
| Sidecar Isolation | Random Unix socket path; not network-accessible; process-level isolation |

PART 3: TECHNICAL SPECIFICATION

Build-Ready Engineering Detail

# 3. Project Structure

forensai/

├─ package.json

├─ electron-builder.yml

├─ vite.config.ts

├─ tsconfig.json

├─ src/

│   ├─ main/                    # Electron main process

│   │   ├─ index.ts             # App entry, window management

│   │   ├─ ipc/                 # IPC handlers (one file per domain)

│   │   ├─ db/                  # Drizzle schema + migrations

│   │   ├─ agents/              # Agent orchestration (4 agents)

│   │   ├─ sidecar/             # Python sidecar lifecycle management

│   │   ├─ services/            # Auth, billing, update, crash reporting

│   │   └─ security/            # PII pipeline, encryption, CSP

│   ├─ renderer/                # React app

│   │   ├─ App.tsx

│   │   ├─ components/          # Reusable UI components

│   │   ├─ features/            # Feature modules

│   │   │   ├─ cases/           # Case list, creation

│   │   │   ├─ explorer/        # Tree navigation

│   │   │   ├─ editor/          # OnlyOffice integration

│   │   │   ├─ gates/           # Gate 1, 2, 3 workflows

│   │   │   ├─ assistant/       # Writing Assistant chat

│   │   │   ├─ settings/        # Configuration UI

│   │   │   └─ onboarding/      # First-run wizard

│   │   ├─ stores/              # Zustand stores

│   │   ├─ hooks/               # Custom React hooks

│   │   └─ styles/              # CSS tokens + themes

│   └─ preload/                 # contextBridge scripts

├─ sidecar/                     # Python PII + style service

│   ├─ main.py                  # JSON-RPC server entry

│   ├─ pii/                     # Presidio + spaCy integration

│   ├─ style/                   # Writing style extraction

│   └─ tests/                   # pytest tests

├─ resources/                   # Seed data

│   ├─ dsm5tr_diagnoses.json

│   ├─ instruments.json

│   └─ report_templates/

└─ tests/                       # E2E tests (Playwright)

# 4. Sprint Plan (MVP: 12 Sprints, 24 Weeks)

Two-week sprints. Each sprint ends with a deployable increment. Your review cadence is built into every sprint.

## Phase 0: Foundation (Sprints 1–4, Weeks 1–8)

Sprint 1: Electron Shell + Database + Auth

- Electron scaffold with Vite bundling

- SQLCipher database with Drizzle ORM schema (all 14 tables, seeded)

- Auth0 PKCE login flow

- Basic window with three-column layout (from v4 prototype CSS)

- contextBridge + preload script with typed IPC

Review: You verify the app launches, login works, database encrypts, layout matches v4 prototype.

Sprint 2: Python Sidecar + PII Pipeline

- Python sidecar with JSON-RPC server over Unix socket

- Presidio + spaCy PII detection (18 HIPAA identifiers)

- Sidecar lifecycle management (spawn, health check, restart)

- PII detection integration tests with synthetic PHI corpus

- PyInstaller frozen build for macOS

Review: You test PII detection with real-format documents (redacted). Verify Safe Harbor coverage.

Sprint 3: Case Management + Document Upload

- Case CRUD (create, list, open, archive)

- Document upload with PDF text extraction (pdf-parse) and DOCX extraction (mammoth)

- Case explorer tree component (from v4 prototype)

- Tab management system

- File storage in SQLCipher blob columns

Review: You create cases, upload documents, browse the explorer tree, open documents in tabs.

Sprint 4: PII Integration + LLM Gateway

- PII detection pipeline: extract text → detect PII → de-identify → store both versions

- Claude API integration with TLS pinning

- API key storage in macOS Keychain (safeStorage)

- Request/response de-identification verification (assert no PHI leaves the app)

- Rate limiting and error handling

GO/NO-GO: PII detection validated against test corpus. If ≥99% recall / <2% false positive → proceed. Otherwise → extend Sprint 4.

## Phase 1: Agents + Gates (Sprints 5–9, Weeks 9–18)

Sprint 5: Ingestor Agent + Gate 1

- Ingestor Agent integration: send de-identified docs to Claude, receive structured JSON

- Re-identification pipeline (replace placeholders with original entities)

- Gate 1 split-view UI: original document viewer (left) + structured data form (right)

- Confirm/correct/flag workflow for each data category

- Audit trail logging for Gate 1 actions

Review: You upload a real-format case, run the Ingestor, confirm data in Gate 1. Assess extraction quality.

Sprint 6: Diagnostician Agent + Gate 2

- Diagnostician Agent: validity assessment, evidence mapping, differential diagnosis

- Gate 2 UI: diagnosis cards with evidence maps

- Decision controls: Render / Rule Out / Defer (no Accept All)

- Clinical notes per decision

- Validity banner (flags concerning scales)

Review: You review evidence maps for test case. Make diagnostic decisions. Assess mapping quality.

Sprint 7: Writer Agent + OnlyOffice Editor

- Writer Agent: generate report from Gate 1 data + Gate 2 decisions + style rules

- Streaming response display (progress indicator during generation)

- OnlyOffice Document Server integration: local service, iframe embed, document API

- AI-generated report saved as .docx and opened in OnlyOffice editor

- AI draft sections marked with Word comments and styled content blocks

- Voice matching using extracted style rules

Review: You read the generated report in OnlyOffice. Assess voice fidelity, clinical accuracy, section completeness. Edit directly.

Sprint 8: Editor Agent + Gate 3

- Editor/Legal Reviewer Agent: vulnerability scanning

- Flags rendered as native Word comments in OnlyOffice

- Gate 3 UI: flag review (accept/dismiss/edit)

- Attestation signature flow

- Report finalization: lock, hash (SHA-256)

- Export: .docx (via docx-js) and PDF

Review: You complete a full end-to-end case. Upload → Ingestor → Gate 1 → Diagnostician → Gate 2 → Writer → Editor → Gate 3 → Export. This is your first full-flow validation.

Sprint 9: Style Extraction + Onboarding

- Writing sample upload (3–5 .docx files)

- Style extraction pipeline (sidecar + Claude analysis)

- First-run onboarding wizard: login → practice profile → sample upload → diagnosis config

- Settings page (diagnosis catalog, instrument library, template selection)

- Writing Assistant chat panel (contextual AI Q&A)

Review: You run onboarding end-to-end. Upload your own writing samples. Verify style extraction produces usable rules.

## Phase 2: Production Hardening (Sprints 10–12, Weeks 19–24)

Sprint 10: Security Hardening + Billing

- CSP implementation and audit

- Apple Developer ID code signing + notarization

- electron-updater with Ed25519 signature verification

- Stripe integration: subscription check, customer portal

- Auto-lock on inactivity

- npm audit + dependency pinning in CI

Review: You verify code-signed .dmg installs cleanly on a fresh Mac. Test billing flow.

Sprint 11: Quality + Performance

- Vitest unit test suite (target: 80% coverage on agents, PII, gate logic)

- Playwright E2E tests (full case workflow, 3 scenarios)

- Performance optimization: large document handling, agent response caching

- Error handling audit: every API call has fallback, every agent has retry logic

- Sentry integration with de-identified error reporting

- Loading states, error states, empty states for every view

Review: You run the full test suite. Attempt to break things: bad files, network failures, large docs.

Sprint 12: Polish + Launch Prep

- UI polish pass: match v4 prototype pixel-perfect

- Audit trail review: verify completeness, export format

- User documentation: in-app help tooltips, knowledge base articles

- DMG packaging with installer graphics

- Landing page content preparation

- Beta cohort recruitment (5–10 clinicians)

Review: Final pre-launch review. Complete 3 test cases end-to-end. Sign off on MVP.

PART 4: DEVELOPMENT COST ESTIMATE

Token Costs, Conversation Turns, and Timeline

# 5. Development Model

This estimate assumes Truck builds Forensai in collaboration with Claude (Opus), using the working pattern established in prior sessions: rapid decision loops, artifact generation, iterative review. No additional engineers for MVP.

## 5.1 Assumptions

- Claude Opus at $15/MTok input, $75/MTok output (API pricing)

- Claude Pro/Max subscription at $100–$200/month (if using Claude.ai or Claude Code)

- Average conversation turn: ~4K input tokens, ~3K output tokens

- A “session” is a focused 2–4 hour working block producing deployable code

- Each sprint requires 6–10 sessions of Claude collaboration

- Truck reviews and tests between sessions (1–2 hours per review cycle)

- Code generation is the primary use; Claude writes ~80% of implementation code

## 5.2 Per-Sprint Breakdown

### Foundation Sprints (1–4): Heavy scaffolding, high token usage

| Metric | Per Sprint | Phase Total (4 sprints) |
| --- | --- | --- |
| Sessions | 8–10 | 32–40 |
| Conversation turns | 60–80 per session | ~2,400–3,200 |
| Input tokens | ~250K per session | ~8M–10M |
| Output tokens | ~200K per session | ~6.4M–8M |
| Claude API cost | $18–$23 per session | $576–$920 |
| Truck review hours | 4–6 hrs per sprint | 16–24 hrs |

### Agent + Gate Sprints (5–9): Core product, highest complexity

| Metric | Per Sprint | Phase Total (5 sprints) |
| --- | --- | --- |
| Sessions | 10–12 | 50–60 |
| Conversation turns | 70–90 per session | ~3,500–5,400 |
| Input tokens | ~300K per session | ~15M–18M |
| Output tokens | ~250K per session | ~12.5M–15M |
| Claude API cost | $22–$28 per session | $1,100–$1,680 |
| Truck review hours | 6–8 hrs per sprint | 30–40 hrs |

### Hardening Sprints (10–12): Testing, polish, lower generation

| Metric | Per Sprint | Phase Total (3 sprints) |
| --- | --- | --- |
| Sessions | 6–8 | 18–24 |
| Conversation turns | 50–70 per session | ~900–1,680 |
| Input tokens | ~200K per session | ~3.6M–4.8M |
| Output tokens | ~150K per session | ~2.7M–3.6M |
| Claude API cost | $14–$18 per session | $252–$432 |
| Truck review hours | 6–10 hrs per sprint | 18–30 hrs |

## 5.3 Total MVP Cost Estimate

Token Costs (if using API directly)

| Category | Estimate |
| --- | --- |
| Total sessions | 100–124 |
| Total conversation turns | ~6,800–10,280 |
| Total input tokens | ~26.6M–32.8M |
| Total output tokens | ~21.6M–26.6M |
| Input cost ($15/MTok) | $399–$492 |
| Output cost ($75/MTok) | $1,620–$1,995 |
| Total API token cost | $2,019–$2,487 |

Alternative: Claude Pro/Max Subscription

| Plan | Cost for 6 months (MVP timeline) |
| --- | --- |
| Claude Pro ($20/mo) | $120 — but will hit rate limits constantly |
| Claude Max ($100/mo) | $600 — sufficient for most sprints |
| Claude Max ($200/mo) | $1,200 — comfortable headroom for heavy sprints |

Recommendation: Claude Max at $200/mo for the first 3 months (heavy foundation + agent work), drop to $100/mo for hardening sprints. Estimated subscription cost: $900–$1,200 for MVP.

Other Development Costs

| Item | Cost |
| --- | --- |
| Apple Developer Program | $99/year |
| Auth0 (free tier for <7K MAU) | $0 |
| Stripe (2.9% + $0.30 per transaction) | $0 until revenue |
| Sentry (free tier) | $0 |
| GitHub (free tier for private repos) | $0 |
| Domain + hosting (landing page) | $20–$50/year |
| Claude API for production testing | $50–$100 |
| Total non-token dev costs | $169–$249 |

TOTAL MVP DEVELOPMENT COST: $1,069 – $2,736

(Range depends on API vs. subscription model and session efficiency)

## 5.4 Truck’s Time Investment

| Activity | Hours (MVP total) |
| --- | --- |
| Collaborative sessions with Claude | 200–250 hrs (avg 2 hrs/session × 100–124 sessions) |
| Review and testing between sessions | 64–94 hrs |
| Business/legal/compliance (parallel) | 40–60 hrs |
| Beta coordination | 10–20 hrs |
| Total Truck hours | 314–424 hrs over 24 weeks |
| Average weekly commitment | 13–18 hrs/week |

## 5.5 Production LLM Costs (Post-Launch)

Each case processed through Forensai makes 4 Claude API calls (one per agent). Estimated per-case cost:

| Agent | Estimated Tokens / Cost per Case |
| --- | --- |
| Ingestor | ~20K in / ~10K out = $0.30 + $0.75 = $1.05 |
| Diagnostician | ~15K in / ~8K out = $0.23 + $0.60 = $0.83 |
| Writer | ~25K in / ~15K out = $0.38 + $1.13 = $1.51 |
| Editor | ~20K in / ~8K out = $0.30 + $0.60 = $0.90 |
| Total per case | ~$4.29 |
| At 100 users, 10 cases/mo each | ~$4,290/mo LLM cost |
| Revenue at $149/mo × 100 users | $14,900/mo |
| LLM cost as % of revenue | ~29% (improves with volume pricing) |

## 5.6 Timeline Summary

| Phase | Sprints | Calendar |
| --- | --- | --- |
| Phase 0: Foundation | Sprints 1–4 | Weeks 1–8 |
| PII GO/NO-GO Gate | — | End of Week 8 |
| Phase 1: Agents + Gates | Sprints 5–9 | Weeks 9–18 |
| Full-Flow Review | — | End of Week 16 |
| Phase 2: Hardening | Sprints 10–12 | Weeks 19–24 |
| MVP Launch | — | Week 24 (September 2026) |

Start date: March 24, 2026. Target MVP launch: September 5, 2026.

# 6. Post-MVP Roadmap

The MVP architecture supports direct continuation into these phases without rewrite:

| Version | Features Added |
| --- | --- |
| v1.0.1 (Oct 2026) | Windows build + auto-updater; Linux AppImage |
| v1.1 (Nov 2026) | Whisper transcription; psychometrist role; psycho-legal analysis (Dusky, M’Naghten); case search/filter; PHI Review Queue |
| v1.2 (Jan 2027) | Testimony prep export; custom instruments; multi-case dashboard; advanced audit trail |
| v2.0 (Q2 2027) | Shared network storage (ADR-001 Mode 2); offline mode with sync; multi-user collaboration |
| v3.0 (Q4 2027) | Cloud storage (ADR-001 Mode 3); SharePoint/Google Drive integration; enterprise features |

# 7. Risk Register

| Risk | Probability | Mitigation |
| --- | --- | --- |
| PII detection fails Safe Harbor | Medium | Sprint 4 GO/NO-GO gate; fallback to stricter rules; engage clinical advisor |
| FDA classifies as SaMD | Low | External counsel review (Phase 0 parallel); CDS exemption analysis already drafted |
| Test publisher IP objection | Medium | IP counsel audit; instrument data sourced from clinician’s own score reports only |
| OnlyOffice Community AGPL licensing concern | Low | AGPL is fine for local desktop server; Developer Edition upgrade path at $1.5–2.4K/yr if needed |
| Claude API cost exceeds margin | Low | Negotiate enterprise pricing at scale; optimize prompts; cache repeated patterns |
| Beta clinicians reject workflow | Medium | Sprint 8 full-flow review; iterative feedback; “doctor always diagnoses” is differentiator not friction |
| macOS Gatekeeper blocks app | Low | Code signing + notarization in Sprint 10; tested on clean Mac |